## Job Log
Redd Brothers Construction
Job Profitability Tracker — 2026
| Total Jobs: | 12
| Completed Jobs: | 7
| Avg Margin: | 27.1%
| Best Job: | Heritage Apartments
| Worst Job: | Tom Petrosky
| Total Profit (completed): | 25354.05
Job # | Client | Job Description | Status | Quoted Price | Materials | Labor Hrs | Labor Cost | Subcontractor | Other Costs | Total Actual | Profit | Margin % | Notes
JB-2601 | Dave Kowalski | Kitchen remodel - cabinets, countertops, backsplash | done | 28500 | 11247.83 | 142 | 6390 | 3800 | 425 | 21862.83 | 6637.17 | 23.29% | came in under, Dave wants to do bathroom next
JB-2602 | Sarah & Mike Chen | Deck build - 16x20 composite | done | 18000 | 8945 | 96 | 4320 |  | 267 | 13532 | 4468 | 24.82% | permit took 3 weeks, delayed start
JB-2603 | Meridian Church | Bathroom ADA retrofit x2 | done | 22000 | 7823.4 | 118 | 5310 | 2100 | 890 | 16123.4 | 5876.6 | 26.71% | non-profit, gave them a break on price
JB-2604 | Tom Petrosky | Basement finishing - framing, drywall, LVP, egress window | done | 35000 | 17892.17 | 203 | 9135 | 6300 | 2440 | 35767.17 | -767.17 | -2.192% | client added scope mid-job, should have re-quoted
JB-2605 | Linda Ferraro | Fence - 180 LF cedar privacy 6ft | done | 12500 | 5430 | 54 | 2430 |  | 180 | 8040 | 4460 | 35.68%
JB-2606 | Heritage Apartments | Unit turnover - paint, patch, fixtures (unit 4B) | done | 4200 | 823.55 | 28 | 1260 |  | 95 | 2178.55 | 2021.45 | 48.13% | quick job, they have 3 more units coming
JB-2607 | Dave Kowalski | Master bath - tile, vanity, lighting | active | 19500 | 6100 | 67 | 3015 | 2400 | 350 | 11865 | 7635 | 39.15% | waiting on vanity backorder, ETA 4/22
JB-2608 | First Methodist Daycare | Playground fence + gate install | done | 8000 | 3412 | 38 | 1710 |  | 220 | 5342 | 2658 | 33.23%
JB-2609 | Carla Briggs | Garage conversion to home office | active | 24000 | 4890 | 45 | 2025 | 1600 |  | 8515 | 15485 | 64.52% | just started demo, inspection scheduled 4/18
JB-2610 | Heritage Apartments | Unit turnover - unit 7A, bigger scope than 4B | active | 5800 | 340 | 8 | 360 |  |  | 700 | 5100 | 87.93% | just started
JB-2611 | Jim & Pat Deluca | Whole-house interior paint | on hold | 7500 | [8 empty] | on hold, they're dealing with insurance claim from water damage
JB-2612 | Dave (referral from Tom) | Shed build - 12x16 with electrical | on hold | 14000 | [8 empty] | waiting on HOA approval, might not happen
---
shop rate is $45/hr, need to bump to $50 in Q3
Heritage wants a bulk deal for remaining units, think about 10% discount
last updated 4/13

## Rates & Assumptions
Shop rate ($/hr) | 45
Target margin | 25%
Insurance monthly | 485
Truck payment | 487
Material markup % | n/a - we pass through at cost
notes
Tom wants to renegotiate rate for Q3
check workers comp renewal date