## Deal Inputs
Property Address | 1847 Maple Drive
Purchase Price | 195000
Closing Costs (buy side) | 3500
Earnest Money | 5000
Financing Type | Hard Money
Loan-to-Cost (%) | 85%
Loan Amount | 223380
Cash Out of Pocket | 42920
Interest Rate (annual) | 12%
Points (origination) | 2
Point Cost ($) | 4467.6
Estimated Hold Period (months) | 5
Monthly Interest Cost | 2233.8
Estimated ARV | 315000
Comp 1 (notes) | -
Comp 2 | -
Comp 3 | -
Avg Comp Price / SqFt | 185
Subject Property SqFt | 1700
ARV per SqFt | 185.2941
Agent Commission (%) | 5%
Agent Commission ($) | 15750
Seller Closing Costs | 3000
Staging / Marketing | 1500
Total Selling Costs | 20250

## Rehab Budget
Category | Description | Est. Cost | Actual Cost | Variance | % of Budget | Status | Notes
Kitchen (cabinets, counters, appliances) | Full kitchen refresh | 18000 |  | -18000 | 26.55%
Bathrooms (2 full, 1 half) | Fixtures + tile | 12000 |  | -12000 | 17.7%
Flooring (LVP throughout) | Main level | 6500 |  | -6500 | 9.587%
Interior Paint | Whole house | 4200 |  | -4200 | 6.195%
Exterior Paint / Siding | Touch-ups | 3800 |  | -3800 | 5.605%
Roof | Not needed | 0 |  | 0 | 0%
HVAC | No change | 0 |  | 0 | 0%
Electrical (panel upgrade, fixtures) | Panel + LED | 3200 |  | -3200 | 4.72%
Plumbing (2 fixtures + water heater) | HW heater | 4500 |  | -4500 | 6.637%
Windows (6 replaced) | Efficiency | 4800 |  | -4800 | 7.08%
Landscaping / Curb Appeal | Mulch + beds | 2500 |  | -2500 | 3.687%
Permits & Inspections | Permit fees | 1200 |  | -1200 | 1.77%
Dumpster & Cleanup | 3 pulls | 900 |  | -900 | 1.327%
Contingency (10-15%) | Buffer | 6200 |  | -6200 | 9.145%
| Total Estimated | 67800 | 0 | -67800
| Budget Remaining | 67800
| % Complete (by cost) | 0%

## Holding Costs
Cost Category | Monthly Cost | Months | Total
Loan Interest | 2233.8 | 5 | 11169
Property Tax | 320 | 5 | 1600
Insurance (vacant/builder) | 175 | 5 | 875
Utilities | 280 | 5 | 1400
Lawn / Snow / Maintenance | 100 | 5 | 500
HOA | 0 | 5 | 0
Security / Monitoring | 0 | 5 | 0
Other | 0 | 5 | 0
TOTALS | 3108.8 |  | 15544

## Profit Analysis
Line | Label | Amount
1 | Purchase Price | 195000
2 | Closing Costs (buy) | 3500
3 | Rehab Budget (est.) | 67800
4 | Loan Points / Origination | 4467.6
5 | Holding Costs | 15544
6 | Selling Costs | 20250
| Total Project Cost | 306561.6
| After-Repair Value | 315000
| Total Project Cost | 306561.6
| Net Profit | 8438.4
| ROI (on total project cost) | 2.753%
| ROI (on cash invested) | 19.66%
| Annualized ROI (cash) | 47.19%
| Profit per Month | 1687.68
| 70% Rule Max Offer | 152700
| Passes 70% rule? | FAIL
| Target Profit Margin (input) | 15%
| Target Profit ($) | 47250
| MAO (simple) | 164156
| Actual Profit Margin | 2.679%
Sensitivity: Net Profit
|  | ARV -10% | ARV -5% | ARV (base) | ARV +5% | ARV +10%
| Rehab +20% | -36621.6 | -20871.6 | -5121.6 | 10628.4 | 26378.4
| Rehab +10% | -29841.6 | -14091.6 | 1658.4 | 17408.4 | 33158.4
| Rehab (base) | -23061.6 | -7311.6 | 8438.4 | 24188.4 | 39938.4
| Rehab -10% | -16281.6 | -531.6 | 15218.4 | 30968.4 | 46718.4
| Rehab -20% | -9501.6 | 6248.4 | 21998.4 | 37748.4 | 53498.4

## Timeline
Week # | Date Range (fill in) | Phase | Key Tasks | Est. Spend Week | Cumulative Spend | Status
1 | Close / acquisition | Acquisition | Close on property | 3500 | 3500 | In Progress
2 | Demo start | Demo | Kitchen + bath demo | 4000 | 7500
3 | Demo cont. | Demo | Debris out | 1200 | 8700
4 | Rough-in | Rough-In | Electrical/plumbing rough | 5500 | 14200 | Delayed
5 | Rough-in | Rough-In | Inspect rough | 800 | 15000
6 | Drywall | Rough-In | Hang + mud | 6200 | 21200
7 | Paint | Finishes | Interior paint | 4200 | 25400
8 | Flooring | Finishes | LVP install | 6500 | 31900
9 | Kitchen | Finishes | Cabinets + counters | 12000 | 43900
10 | Baths | Finishes | Fixtures + tile | 9000 | 52900
11 | Punch list | Punch List | Touch-ups | 1500 | 54400
12 | Listing prep | Listing | Clean + stage | 1800 | 56200
13 | Live | Listing | Photos + listing | 600 | 56800
14 | On market | Under Contract | Showings | 0 | 56800
15 | On market | Under Contract | Price tweak | 0 | 56800
16 | UC | Under Contract | Inspection response | 900 | 57700
17 | UC | Under Contract | Appraisal | 0 | 57700
18 | UC | Closing | Title + walkthrough | 500 | 58200
19 | Closing | Closing | Final walk | 0 | 58200
20 | Closed | Closing | Recording | 300 | 58500